## Example
RISK ANALYSIS TABLE FOR CONDO MANAGEMENT SYSTEM
Last Update: 04/02/2024
Risk ID | Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Impact of Risk | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
R-1 | 9 - Medium | Unauthorized access to User's Profile | - User has a weak password - Sign up does not enforce complex password format - The passwords stored in the database are not encrypted - No multi-factor authentication | - Cyber attacks are common in in software that handles properties and finances - User's use unsecured public network | To be subjected to unauthorized access to user's sensitive data | 2 | 5 | - data breaches - financial losses - loss of trust in software - legal consequences | - Monitor unusual user activities - Warn users of potential cyber attacks when creating an account | - Implement strong password requirement when user signs up - Implemented strong encryption for passwords - Implement multi-factor authentication | 6 - Low
R-2 | 16 - High | Insufficient system testing | - The test coverage is low which causes undetected bugs and system failures - Inadequate compatibility testing - Incomplete exeption and error handling - Incomplete security testing | - Insufficient testing caused by tight sprint deadlines - Testing inefficient because of frequent changes in the code | To be subjected to software crashes and security vulnerabilities | 5 | 4 | - software crashing when user tries to use a funtionality - software showing invalid output - customer dissatisfaction - software malfunctioning | - Allow users to report bugs on the application/website - Train the entire team on software testing and bug reporting | - Write unit, integration and system tests - Reserve five days before deadline for system testing and fixing bugs and error handling - Attain a test coverage of 80% | 8 - Medium
R-3 | 6 - Low | Data Breach | - Data stored not encrypted and protected - No network security | - Increasing number of cyber threats - Data privacy is important for clients - Fraud and cybercrimes are common | To be subjected to unauthorized access to sensitive data and legal consequences | 2 | 4 | - unauthorized access to sensitive information - loss of trust from customers - legal consequences - cyber attacks - data manipulation - compromising business data | - Aknowledge cyber attacks - Communication methods to warn clients about their account - Establish a cyber attack response plan | - Protect and encrypt data - Train a team member on cybersecurity - Monitor cyber attacks | 4 - Low
R-4 | 4 - Low | Poor communication within team | - Difficult to track the status of project because teammates are not reporting their progress - Difficult to set up meeting with all teammates because of conflicting schedules - Important information not shared | - Fast paced project - Changes in the project requirements | To be subjected to misunderstanding and conflicts among teammates | 2 | 4 | - reduced productivity - misunderstanding in teams - duplicated efforts - project goals not aligned - delays in decision-making | - Document communication challenges - Document teammates feedback | - Establish meeting every three days to update on the project - Have a group chat where teammates text updates about their tasks - Share important information on the group chat | 2 - Very low
R-5 | 25 - Critical | Unqualified teammates for mobile app development | - Teammates consists of web development professional and are unfamiliar with mobile application development and frameworks - Teammates don't have understanding of mobile design and coding | - Mobile applications are preferred over websites because it is easily accesible - Mobile applications are more popular and used than websites | To be subjected in a delay in developing mobile application | 5 | 5 | - project delivery delays - slow development pace - increased risk of errors - reduced quality of application | - Use cross platform frameworks like React Native - Prioritize core features development of app | - Train the team in mobile application development and speacialize in a framework - Divide the team into a web development team and application development team - Implement testing plan on mobile application | 8 - Medium
R-6 | 8 - Medium | Poor requirements definition | - Stakeholder not actively involved - Requirements are ambiguous which can lead to misunderstanding | - Difficult access of potential users for feedback - Frequent changes in the requirements | To be subject of project delays, rework and quality problems | 2 | 4 | - lack of clarity - misunderstandings and dissatisfaction among stakeholders - misinterpretation of requirements by the development team | - Get the most information possible when meeting stakeholder - Document meetings | - Meet the stakeholder weekly for project review and progress - Prepare adequate documentation for requirement analysis | 2 - Very low
R-7 | 10 - Medium | Condo owner dashboard displaying incomplete or inacurate information | - correct data not saved in the database properly - there is invalid data asserted in the database - the interface is not clear | - Data innacuracy are common because of improper input validation | To be subject of unreliable data in database | 2 | 5 | - data innacuracy and errors in the software - comprimised data integrity will make a untrusthy software - incorrect outputs | - monitor the database and check for invalid data | - Implement strict data validation rules - The database administrator should regulary review and clean the database to remove invalid data | 6 - Low
R-8 | 25 - Critical | User forgets password and is not able to access their account | - unable to retrieve acount information | - users often forget their password because they have soo many passwords and accounts to remember these days | To be subjected of loss of access to crucial account information and data | 5 | 3 | - loss of access - decreased user engagement - negative user experience - security risks | - Make the user call customer service to retrieve their password and ask the user to reset | - Implement a "forget password" that will help user reset their password and have access to their account | 3 - Very low
R-9 | 6 - Low | Managing large numbers of documents | - documents that are uploaded are not saved correctly | - documents like pdf files can be difficult to store in the database | To be subjected of difficulty uploading and opening documents | 2 | 3 | - loss of access of important documents - finacial losses and confusion for condo management companies - time wasted | - Make the user print a copy of the document as backup - display a warning message that the files might not be saved successfully | - Implement a document verification process to ensure that they are successfully saved. - Update the database memory space | 8 - Medium
R-10 | 4 - Low | Data access violation for condo management companies information | - unauthorized users have access to condo management companies properties information | - Unproper data access and protections | To be subjected of crucial data leak | 2 | 3 | - violation of privacy - financial loss - theft and fraud - reputation damage | - Manually test the system as all possible users to report any bugs | - Implement a extra security level to have access to condo management companies properties information such as access key | 3 - Very low
R-11 | 16 - High | There is a lack of time management and organization within the developer team. This results in all teammates working on the project a few days before the deadline | - we are unable to implement all the functionalities documented in the release plan - project delays | - the developer team are busy students taking many classes and have different priorities | To be subjected delivery delays | 5 | 4 | - deadlines unmet - bad software quality - project delays - accumulting tasks | - split tasks in an efficient way so that people available early in the sprint can work on frontend and documentation tasks - divide the sprint in weeks like first week: frontend second week: backend, last week: documentatiom+testing | - the developer team reserves 5 hours each week to meet up and work on the project | 3 - Very low
R-12 | 8 - Medium | Some teammates of the developer team are unable to connect to the database. Therefore, they cannot test the website and detect errors related to database operations | - people writing code without being sure that it works correctly | - configuring a database can be difficult we need to create the table and write data ourselves | To be subjected of time ineficiency | 2 | 3 | - coding backend becomes challenging when there isn't a database convention - backend team using different reference values - messy code | - create a group of backend developers who maintains and manages databases | - write a script to initialize all tables and add values to them - the team can later go on pgAdmin and see the schemas and tables | 3 - Very low
R-13 | 4 - Low | The code repository is becoming very complex and disorganized because people are commiting without following a file organization convention | - The developer team are unable to find a specific file easily because the directories are confusing | - Repo structure conventions were not defined in the beginning of the project | To be subjected of disorganized and confusing repository | 2 | 3 | - Developers don't know where to add they new files - takes time finding a specific file or component | - Let the developers refactor the code as they work on their code | - Assign a developer to refactor the entire repository and inform the team of conventions - Give the repository a clear and understandable structure | 3 - Very low