## Condo management project - View
Title | URL | Estimate | Labels
As a condo management company, I want to access the details of my property from the mobile app | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/163 |  | Mobile, User Story
Implement overview of properties UI page | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/164 | 2 | development, frontend, Mobile, task
Implement property details UI page | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/165 | 3 | development, frontend, Mobile, task
As a condo owner or rental user, I want to reserve common facilities in a calendar-like interface. | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/63 |  | Mobile, tasks TBA, User Story, Web
Add backend code to fetch reservations by facility | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/156 | 2 | backend, development, task, Web
Create parking space overview page. | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/106 | 3 | development, frontend, task, Web
Create frontend page for reservations | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/155 | 3 | development, frontend, task, Web
Add backend implementation to save reservations | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/154 | 2 | backend, development, task, Web
Add db tables for reservations | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/153 | 1 | database, development, task, Web
As a user, I want to access the details of my profile | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/161 |  | Mobile, User Story
Implement profile page UI | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/162 | 2 | development, frontend, Mobile, task
As a user, I want to access my account on the mobile version of the platform | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/157 |  | Mobile, User Story
Add a home page for the app | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/160 | 2 | development, frontend, Mobile, task
Implement Signup UI | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/159 | 2 | development, frontend, Mobile, task
Implement login UI | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/158 | 2 | development, frontend, Mobile, task
Carryover tasks from past sprints, reevaluated
As a condo management company, I want to set up the condo fee per square foot and per parking spot and calculate condo fees for each unit. | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/50 |  | tasks TBA, User Story, Web
Add backend code for parking fee update | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/111 | 2 | backend, development, task, Web
Add fields to unit table | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/112 | 1 | database, development, task, Web
Modify the unit overview page | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/113 | 2 | development, frontend, task, Web
Add backend code for unit field updates | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/114 | 2 | backend, development, task, Web
Create backend code to return total expense for a user. | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/115 | 3 | backend, development, task, Web
Update financial status page | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/116 | 2 | development, frontend, task, Web
Add link of parking page for a property | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/105 | 1 | development, frontend, task, Web
Total |  | 37
Sprint Burndown Chart
Assuming we start on the 25th, we will have 17 days in this sprint.
Total Story Points = 37
Ideal Daily Burndown Rate = 37/17 = 2.17 USP