## Example
RISK ANALYSIS TABLE FOR CONDO MANAGEMENT SYSTEM
Last Update: 04/02/2024
Risk ID | Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Impact of Risk | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
R-1 | 9 - Medium | Unauthorized access to User's Profile | - User has a weak password - Sign up does not enforce complex password format - The passwords stored in the database are not encrypted - No multi-factor authentication | - Cyber attacks are common in in software that handles properties and finances - User's use unsecured public network | To be subjected to unauthorized access to user's sensitive data | 2 | 5 | - data breaches - financial losses - loss of trust in software - legal consequences | - Monitor unusual user activities - Warn users of potential cyber attacks when creating an account | - Implement strong password requirement when user signs up - Implemented strong encryption for passwords - Implement multi-factor authentication | 6 - Low
R-2 | 16 - High | Insufficient system testing | - The test coverage is low which causes undetected bugs and system failures - Inadequate compatibility testing - Incomplete exeption and error handling - Incomplete security testing | - Insufficient testing caused by tight sprint deadlines - Testing inefficient because of frequent changes in the code | To be subjected to software crashes and security vulnerabilities | 5 | 4 | - software crashing when user tries to use a funtionality - software showing invalid output - customer dissatisfaction - software malfunctioning | - Allow users to report bugs on the application/website - Train the entire team on software testing and bug reporting | - Write unit, integration and system tests - Reserve five days before deadline for system testing and fixing bugs and error handling - Attain a test coverage of 80% | 8 - Medium
R-3 | 6 - Low | Data Breach | - Data stored not encrypted and protected - No network security | - Increasing number of cyber threats - Data privacy is important for clients - Fraud and cybercrimes are common | To be subjected to unauthorized access to sensitive data and legal consequences | 2 | 4 | - unauthorized access to sensitive information - loss of trust from customers - legal consequences - cyber attacks - data manipulation - compromising business data | - Aknowledge cyber attacks - Communication methods to warn clients about their account - Establish a cyber attack response plan | - Protect and encrypt data - Train a team member on cybersecurity - Monitor cyber attacks | 4 - Low
R-4 | 4 - Low | Poor communication within team | - Difficult to track the status of project because teammates are not reporting their progress - Difficult to set up meeting with all teammates because of conflicting schedules - Important information not shared | - Fast paced project - Changes in the project requirements | To be subjected to misunderstanding and conflicts among teammates | 2 | 4 | - reduced productivity - misunderstanding in teams - duplicated efforts - project goals not aligned - delays in decision-making | - Document communication challenges - Document teammates feedback | - Establish meeting every three days to update on the project - Have a group chat where teammates text updates about their tasks - Share important information on the group chat | 2 - Very low
R-5 | 25 - Critical | Unqualified teammates for mobile app development | - Teammates consists of web development professional and are unfamiliar with mobile application development and frameworks - Teammates don't have understanding of mobile design and coding | - Mobile applications are preferred over websites because it is easily accesible - Mobile applications are more popular and used than websites | To be subjected in a delay in developing mobile application | 5 | 5 | - project delivery delays - slow development pace - increased risk of errors - reduced quality of application | - Use cross platform frameworks like React Native - Prioritize core features development of app | - Train the team in mobile application development and speacialize in a framework - Divide the team into a web development team and application development team - Implement testing plan on mobile application | 8 - Medium
R-6 | 8 - Medium | Poor requirements definition | - Stakeholder not actively involved - Requirements are ambiguous which can lead to misunderstanding | - Difficult access of potential users for feedback - Frequent changes in the requirements | To be subject of project delays, rework and quality problems | 2 | 4 | - lack of clarity - misunderstandings and dissatisfaction among stakeholders - misinterpretation of requirements by the development team | - Get the most information possible when meeting stakeholder - Document meetings | - Meet the stakeholder weekly for project review and progress - Prepare adequate documentation for requirement analysis | 2 - Very low
R-7 | 10 - Medium | Condo owner dashboard displaying incomplete or inacurate information | - Correct data not saved in the database properly - there is invalid data asserted in the database - the interface is not clear | - Data innacuracy are common because of improper input validation | To be subject of unreliable data in database | 2 | 5 | - data innacuracy and errors in the software - comprimised data integrity will make a untrusthy software - incorrect outputs | - monitor the database and check for invalid data | - Implement strict data validation rules - The database administrator should regulary review and clean the database to remove invalid data | 6 - Low
R-8 | 25 - Critical | User forgets password and is not able to access their account | - Unable to retrieve acount information | - users often forget their password because they have soo many passwords and accounts to remember these days | To be subjected of loss of access to crucial account information and data | 5 | 3 | - loss of access - decreased user engagement - negative user experience - security risks | - Make the user call customer service to retrieve their password and ask the user to reset | - Implement a "forget password" that will help user reset their password and have access to their account | 3 - Very low
R-9 | 6 - Low | Managing large numbers of documents | - Documents that are uploaded are not saved correctly | - documents like pdf files can be difficult to store in the database | To be subjected of difficulty uploading and opening documents | 2 | 3 | - loss of access of important documents - finacial losses and confusion for condo management companies - time wasted | - Make the user print a copy of the document as backup - display a warning message that the files might not be saved successfully | - Implement a document verification process to ensure that they are successfully saved. - Update the database memory space | 8 - Medium
R-10 | 4 - Low | Data access violation for condo management companies information | - Unauthorized users have access to condo management companies properties information | - Unproper data access and protections | To be subjected of crucial data leak | 2 | 3 | - violation of privacy - financial loss - theft and fraud - reputation damage | - Manually test the system as all possible users to report any bugs | - Implement a extra security level to have access to condo management companies properties information such as access key | 3 - Very low
R-11 | 16 - High | There is a lack of time management and organization within the developer team. This results in all teammates working on the project a few days before the deadline | - Being unable to implement all the functionalities documented in the release plan - project delays | - the developer team are busy students taking many classes and have different priorities | To be subjected delivery delays | 5 | 4 | - deadlines unmet - bad software quality - project delays - accumulting tasks | - split tasks in an efficient way so that people available early in the sprint can work on frontend and documentation tasks - divide the sprint in weeks like first week: frontend second week: backend, last week: documentatiom+testing | - the developer team reserves 5 hours each week to meet up and work on the project | 3 - Very low
R-12 | 8 - Medium | Some teammates of the developer team are unable to connect to the database. Therefore, they cannot test the website and detect errors related to database operations | - People writing code without being sure that it works correctly | - configuring a database can be difficult we need to create the table and write data ourselves | To be subjected of time inefficiency | 2 | 3 | - coding backend becomes challenging when there isn't a database convention - backend team using different reference values - messy code | - create a group of backend developers who maintains and manages databases | - write a script to initialize all tables and add values to them - the team can later go on pgAdmin and see the schemas and tables | 3 - Very low
R-13 | 4 - Low | The code repository is becoming very complex and disorganized because people are commiting without following a file organization convention | - The developer team are unable to find a specific file easily because the directories are confusing | - Repo structure conventions were not defined in the beginning of the project | To be subjected of disorganized and confusing repository | 2 | 3 | - Developers don't know where to add they new files - takes time finding a specific file or component | - Let the developers refactor the code as they work on their code | - Assign a developer to refactor the entire repository and inform the team of conventions - Give the repository a clear and understandable structure | 3 - Very low
R-14 | 6 - Low | Data Migration Errors Leading to Data Loss or Corruption | - Incompatible data format - Data mapping errors - Incomplete data backup | - Data Volume and Complexity - Cloud Service Provider Capabilities | To be subjected to loss of crucial data | 2 | 3 | - Users can't find relevant and important information about their condo unit - Condo Building Company can't find important and relevant information about their condo buildings - Condo owners can't find important and relevant information on their condo building - Payment information may get lost, which could lead to financial issues | - Monitor the data for missing or lost data | - Double check the data implementation and formatting to ensure that it won't lead to any errors during the migration - Backup the data for retrieval if ever it gets lost during migration | 8 - Medium
R-15 | 4 - Low | Inadequate Scalability Planning Leading to Performance Issues | - Lack of Performance Testing - Incorrect estimation of expected user traffic, data volumes, or transaction rates | - An influx of user acquisition of this software application - At each important period when users need to use the app to access important information. For example, when monthly payments are due. Another instance would be during the summer season when people are most likely to move in and out of condos | To be subjected to poor performance and even service crash | 1 | 2 | - Service crash on the mobile app and/or website - Slow responses from the mobile app and/or website | - Monitor and alert when performance issues arise | - Regular performance testing - Define tolerance levels for the performance | 3 - Very low