## Example
RISK ANALYSIS TABLE FOR CONDO MANAGEMENT SYSTEM
Last Update: 04/02/2024
Risk ID | Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
1 | 9 - Medium | Unauthorized access to User's Profile | - User has a weak password - Sign up does not enforce complex password format - The passwords stored in the database are not encrypted - No multi-factor authentication | - Cyber attacks are common in in software that handles properties and finances - User's use unsecured public network | To be subjected to unauthorized access to user's sensitive data | 2 | 5 | - Monitor unusual user activities - Warn users of potential cyber attacks when creating an account | - Implement strong password requirement when user signs up - Implemented strong encryption for passwords - Implement multi-factor authentication | 6 - Low
2 | 16 - High | Insufficient system testing | - The test coverage is low which causes undetected bugs and system failures - Inadequate compatibility testing - Incomplete exeption and error handling - Incomplete security testing | - Insufficient testing caused by tight sprint deadlines - Testing inefficient because of frequent changes in the code | To be subjected to software crashes and security vulnerabilities | 5 | 4 | - Allow users to report bugs on the application/website - Train the entire team on software testing and bug reporting | - Write unit, integration and system tests - Reserve five days before deadline for system testing and fixing bugs and error handling - Attain a test coverage of 80% | 8 - Medium
3 | 6 - Low | Data Breach | - Data stored not encrypted and protected - No network security | - Increasing number of cyber threats - Data privacy is important for clients - Fraud and cybercrimes are common | To be subjected to unauthorized access to sensitive data and legal consequences | 2 | 4 | - Aknowledge cyber attacks - Communication methods to warn clients about their account - Establish a cyber attack response plan | - Protect and encrypt data - Train a team member on cybersecurity - Monitor cyber attacks | 4 - Low
4 | 4 - Low | Poor communication within team | - Difficult to track the status of project because teammates are not reporting their progress - Difficult to set up meeting with all teammates because of conflicting schedules - Important information not shared | - Fast paced project - Changes in the project requirements | To be subjected to misunderstanding and conflicts among teammates | 2 | 4 | - Document communication challenges - Document teammates feedback | - Establish meeting every three days to update on the project - Have a group chat where teammates text updates about their tasks - Share important information on the group chat | 2 - Very low
5 | 25 - Critical | Unqualified teammates for mobile app development | - Teammates consists of web development professional and are unfamiliar with mobile application development and frameworks - Teammates don't have understanding of mobile design and coding | - Mobile applications are preferred over websites because it is easily accesible - Mobile applications are more popular and used than websites | To be subjected in a delay in developing mobile application | 5 | 5 | - Use cross platform frameworks like React Native - Prioritize core features development of app | - Train the team in mobile application development and speacialize in a framework - Divide the team into a web development team and application development team - Implement testing plan on mobile application | 8 - Medium
6 | 8 - Medium | Poor requirements definition | - Stakeholder not actively involved - Requirements are ambiguous which can lead to misunderstanding | - Difficult access of potential users for feedback - Frequent changes in the requirements | To be subject of project delays, rework and quality problems | 2 | 4 | - Get the most information possible when meeting stakeholder - Document meetings | - Meet the stakeholder weekly for project review and progress - Prepare adequate documentation for requirement analysis | 2 - Very low
CONFIDENTIAL