## Sheet1
ENGR 390 - Team 07
Traceability Matrix
Project Name |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Condo360 |  | Jan.23 - Feb.07 | Feb.08 - Feb.28 | Feb.29 - Mar.21 | Mar.22 - Apr.11 | Apr.12 - May.01
Requirement ID | Feature ID | Feature Description | Feature Type | Started in | Finished in | Status | Git Issue | Pull Requests | Test Case
Public Users
1, 2 | 40 | Set up a profile | Profile | Sprint 2 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/40 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/120 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/blob/Dev/next_project/__tests__/ProfileCompletion.test.tsx , https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/blob/Dev/next_project/__tests__/signupCompleteAction.test.tsx | .
3, 4 | 41 | Provide a registration key | Property | Sprint 3 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/41 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/204 | -
Condo Owners | [9 empty] | .
5, 13 | 42 | Properties dashboard | Dashboard | Sprint 2 | Sprint 2 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/42 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/101 | -
24 | 43 | Status of submitted requests | Requests | Sprint 3 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/43 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/173 | -
24 | 44 | Notifications of latest activities | Requests | Sprint 5 | Sprint 5 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/44 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/231 | -
5, 19 | 56 | Available common facility | Reservation System | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/56 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/149 | -
16, 18 | 57 | FIFO reservation system | Reservation System | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/57 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/149 | -
18 | 63 | Reserve common facilities | Reservation System | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/63 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/208 | -
Condo Management Companies
6 | 62 | Overview of owned properties | Dashboard | Sprint 2 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/62 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/101 | -
15 | 53 | Financial annual report | Financial System | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/53 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/141 | -
6, 7 | 45 | Create profiles for properties | Property | Sprint 2 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/45 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/122 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/blob/Dev/next_project/__tests__/HandleLockerRegistration.test.tsx | .
11 | 52 | Enter cost for operations | Financial System | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/52 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/109 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/blob/Dev/next_project/__tests__/getSalesByCompanyId.test.tsx | .
9 | 47 | Condo units information | Dashboard | Sprint 3 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/47 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/204 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/blob/Dev/next_project/__tests__/getunit.test.tsx | .
14 | 51 | Operational buddget and costs | Financial System | Sprint 3 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/51 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/204 | -
10 | 48 | Send registration keys | Property | Sprint 3 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/48 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/204 | -
16, 17 | 54 | Set up reservations for facilities | Reservation System | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/54 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/167 | -
20 | 49 | Roles for employees | Financial System | Sprint 3 | Sprint 3 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/49 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/204 | -
12, 13 | 50 | Condo fee | Property/Financial System | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/50 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/204 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/blob/Dev/next_project/__tests__/getUnitFreesByUserId.test.tsx | .
8 | 46 | Upload condo files | Property | Sprint 5 | Sprint 5 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/46 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/110 | -
Employees
23 | 217 | Accept/Deny requests | Requests | Sprint 3 | Sprint 4 | Completed | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/217 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/204 | -
Mobile App
28 | 157 | Access public user account | Mobile app | Sprint 4 | Sprint 5 | Ongoing | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/157 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/183 | -
28 | 214 | Access condo owner account | Mobile app | Sprint 4 | Sprint 5 | Ongoing | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/214 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/183 | -
28 | 163 | Access condo management company account | Mobile app | Sprint 4 | Sprint 5 | Ongoing | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/163 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/183 | -
28 | 215 | Access employee account | Mobile app | Sprint 4 | Sprint 5 | Ongoing | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/issues/215 | https://github.com/CONCORDIA-SOEN-390/Condo-Mgmt-Web-App/pull/183 | -
Requirement ID | Requirement
CORE
1 | Public users can create their own (unique) profile. The minimum information needed in a profile is below.
2 | A profile should at least include a profile picture, user name, contact email, phone number.
3 | Public users need to provide a registration key obtained from their condo management company to become condo owners in the system.
4 | Public users need to provide a registration key obtained from their condo management company to become rental users in the system.
5 | Condo owners can have a good view (dashboard) of their properties, including general information, e.g., personal profile, condo information, financial status (i.e., remaining balance in terms of monthly condo fee payments), status of the submitted request, etc.
6 | Condo management companies can create a profile for a property under their management.
7 | The property profile should have at least property name, unit count, parking count, locker count, address.
8 | Condo management companies can upload condo files for each property. The condo files are accessible to all condo owners of that property. Examples of such condo files (in pdf) include condo declarations, annual budgets, board meeting minutes etc.
9 | Condo management companies can enter detailed information for each condo unit, each parking spot, and each locker in a building. Basic information of a condo unit includes unit id, size, unit owner, occupant information (i.e., may be occupied by a rental user instead of the owner), as well condo fee associated with the unit. Basic information of a parking spot (or a locker) includes parking spot id, spot owner, occupant information, and condo fee associated with the parking spot.
10 | Condo management companies can send registration keys to unit owners or rental users for their dedicated units. Such registration key will be used by unit owners or rental users to link a condo unit with their profiles.
11 | The condo management system contains a simplified financial system.
12 | Condo management companies can enter condo fee per square foot, per parking spot.
13 | Condo fee of each unit will be calculated and presented to unit owners.
14 | The financial system records operational budget (i.e., the collected condo fee) and cost. Condo management companies can enter the cost for each operation.
15 | The financial system can generate an annual report. For example, all the condo fee collected for a given year.
16 | The condo management system contains a simplified reservation system.
17 | Condo management companies set up the common facilities, which require reservations. Examples include a sky lounge, a spa fitness.
18 | The reservation system allows condo owners and rental users to reserve common facilities in a calendar-like interface.
19 | The reservation system should show availabilities of common facilities.
20 | Condo management companies can set up different roles for different employees, who are responsible for the same property. Such roles include manager, or someone who is responsible for daily operations, or someone who is responsible for finance.
21 | Condo owners can submit requests.
22 | Examples of such requests include moving in/out (date for reserving elevators), intercom changes, requesting access (fobs, keys), reporting a violation, reporting deficiency found in common areas, or asking a question.
23 | Each request will be assigned to a corresponding employee based on the type of the request.
24 | All the users have a notification page, where they can see the latest activities in submitted or assigned requests.
EXTRA
25 | A forum where users can post and reply.
26 | Events. Users can organize events and invite other occupants to attend.
27 | Discounts, offers. Condo management companies can choose to list coupons/offers that are visible to all unit owners or rental users of one property.
BONUS
28 | The app is accessible on Android, iOS, Linux, MacOS, and Windows.
29 | The app is available in English and, at least, one other language.
30 | The app must allow users to login using their Gmail account or other such account (Single Sign On), possibly offering multiple possibilities.